## engineering
Sr No. | Particulars | SE | 2020-21 | 2021-22 | 2022-2023 | B. E 2023-24 | R. E 2023-24 | B. E 2024-25 | Proportionate | % Achievement (as compared to proportionate budget) | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01
1 | Providing Civil Amenities in BKC | Mr. C.B. Dhokalepatil | 18.78 | 32.88 | 27.54 | 171.4 | 100 | 100 | 50 | 3000% | 14.12 | 15.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Development of Oshiware District Centre (Land Acqusition) | Mr. P. J. Bhangare | 18.93 | 5.72 | 2.43 | 45 | 3.18 | 30 | 15 | 0.826 | 0.27 | 5.95 | 0 | 0 | 1.13 | 5.55 | 12.39 | 12.39 | 0
3 | MUIP (Incl. BKC Conector) | Mr. P. J. Bhangare | 199.09 | 0 | 0 | 132.38 | 0 | 0.15 | 0.075 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0
4 | Extended MUIP - Land Acquisition | Mr. A.B. Dhabe, Mr. A.G. Korgaonkar, Mr. B.H.Chavan, Mr. P.P.Bhandekar, Mr. S.K.Fulari, Mr. V.A. Jambhale, Mr. V.G. Surve, Mr. Y.E. Sakhalkar, Mr. P.J. Bhangare | 722.86 | 734.74 | 730.58 | 1383.81 | 1402.01 | 2460.12 | 1230.06 | 0.23749 | 598.4 | 875.03 | 8.41 | 85.97 | 137.66 | 190.067 | 292.1252 | 306.1052 | 13.98
5 | Mithi River Removal of floating debris | Mr. C.B. Dhokalepatil | 5.01 | 2.45 | 0 | 1.48 | 0.76 | 0 | 0 |  | 0.61 | 0.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Construction at Wadala Truck Terminal | Mr. C.B. Dhokalepatil | 7.04 | 5.75 | 10 | 15 | 5.97 | 15 | 7.5 | 0.032 | 1.74 | 1.75 | 0 | 0 | 0.24 | 0.24 | 0.24 | 0.24 | 0
7 | Mumbai Trans Harbour Link (MTHL) | Mr. A.G. Korgaonkar | 3118.6 | 4352.24 | 4090.33 | 2273.58 | 2097.3 | 817 | 408.5 | 0.093841 | 2243.97 | -16028.84 | 22.11 | 22.11 | 51.08 | 37.8708 | 38.3342 | 39.6742 | 1.34
8 | Construction of Late Balasaheb Thakrey National Memorial Phase I | Mr. P. J. Bhangare | 0 | 46.02 | 82.26 | 42 | 93.3 | 20 | 10 | 1.5227 | 73.38 | 84.58 | 0 | 5.07 | 5.22 | 6.057 | 15.227 | 15.227 | 0
9 | Resettlement & Rehabitation (R&R) | Mr. B.H. Chavan, Mr. S.S. Lokare | 36.26 | 51.03 | 68.26 | 100 | 173.06 | 150 | 75 | 0.90467 | 172.5484 | 183.6484 | 1.85 | 12.84 | 15.27 | 65.3373 | 67.85 | 77.99 | 10.14
10 | Elevated Raod - Shivadi - Worli | Mr. Y.E. Sakhalkar | 0 | 92.81 | 663.64 | 1100.4 | 600 | 600 | 300 | 0.0040667 | 211.57 | 299.82 | 0 | 0.28 | 1.22 | 1.22 | 1.22 | 1.4 | 0.18
11 | Improvement of Roads in Outer Area of MMR | Mr. V.A. Jambhale | 64.43 | 68.17 | 25.58 | 15 | 2.46 | 25 | 12.5 | 0.068921 | 8.65 | 10.06 | 0 | 0.3 | 0.3 | 0.86151 | 0.86151 | 0.86151 | 0
12 | Construction of SCLR Part-1 & 2 | Mr. S.S. Lokare | 0 | 247.57 | 385.5573 | 100 | 166.99 | 35.84 | 17.92 | 5.3013 | 150.08 | 184.72 | 70 | 95 | 95 | 95 | 95 | 95.53 | 0.53
13 | Creation of infrastructure in Growth Centers in MMR | Mr. A.G. Korgaonkar | 0 | 80.55 | 122.9708 | 180 | 203.59 | 250 | 125 | 0.30064 | 185.14 | 198.83 | 0 | 7.19 | 7.53 | 31.59 | 37.58 | 37.58 | 0
14 | Traffic Improvement Project at Chhedanagar Junction | Mr. V.G. Surve | 0 | 43.77 | 34.5684 | 33 | 37.23 | 15 | 7.5 | 1.1907 | 33.93 | 33.93 | 0 | 0.18 | 0.98 | 8.93 | 8.93 | 8.97 | 0.04
15 | Maintenance and Repair of Eastern Expressway | Mr. P. J. Bhangare | 33.17 | 39.32 | 88.06 | 2 | 62.86 | 10 | 5 | 0 | 51.6344 | 51.5629 | 0 | 0 | 0 | 0 | 0 | 7.38 | 7.38
16 | Maintenance and Repair of Western Expressway | Mr. P. J. Bhangare | 67.48 | 99.84 | 90.16 | 18.06 | 38.17 | 5 | 2.5 | 2.8496 | 25.6 | 34.15 | 0 | 5.03 | 6.7 | 7.0941 | 7.1241 | 7.1241 | 0
17 | Construction of building at WTT | Mr. C.B. Dhokalepatil | 0 | 6.17 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Construction of SCLR-BKC 30 Mtr wide DP Road | Mr. S.S. Lokare | 0 | 1.76 | 0.05 | 11 | 0 | 5 | 2.5 | 0 | 0.08 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Const. Of bridge under Jagruti Nagar Metro station | Mr. S.S. Lokare | 0 | 2.4 | 8.9282 | 2 | 9.44 | 1 | 0.5 | 0 | 7.01 | 7.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Infrastructure at Kalina University | Mr. C.B. Dhokalepatil | 0 | 0 | 0 | 50 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Bharatratna Dr.Babasaheb Ambedkar Memorial at Indu Mill | Mr. P. J. Bhangare | 50.77 | 41.39 | 120 | 500 | 73.71 | 600 | 300 | 0.069338 | 42.05 | 47.41 | 3.39 | 3.39 | 7.33 | 7.68 | 20.8013 | 47.5713 | 26.77
22 | Construction of Thane to Borivali Twin tunnel | Mr. V.A. Jambhale | 0 | 0 | 1.42 | 3000 | 2000.84 | 4000 | 2000 | 0.00067 | 1045.75 | 2004.62 | 0 | 1.34 | 1.34 | 1.34 | 1.34 | 1.34 | 0
23 | Construction of flyoverat CSMIA (T1) | Mr. A.B. Dhabe | 0 | 0 | 17.24 | 8 | 29.03 | 30 | 15 | 0.0073333 | 26.68 | 26.68 | 0 | 0.11 | 0.11 | 0.11 | 0.11 | 0.11 | 0
24 | Construction of flyoverat CSMIA (T2) | Mr. A.B. Dhabe | 0 | 0 | 0.07 | 70 | 0 | 25 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Construction of Road from Anand Nagar to Saket | Mr. V.G. Surve | 0 | 0 | 0 | 500 | 0 | 300 | 150 | 0.0086667 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 1.3 | 0
26 | Construction of Costal Roal Balkum to Gaymukh | Mr. V.G. Surve | 0 | 0 | 0 | 500 | 0.21 | 500 | 250 | 0.00472 | 0 | 0 | 0 | 0 | 0 | 1.16 | 1.18 | 1.18 | 0
27 | Construction of Eastern Freeway from Chhedanagar-Ghatkopar to Thane | Mr. V.G. Surve | 0 | 0 | 0 | 500 | 0 | 500 | 250 | 0.00556 | 0 | 0 | 0 | 0 | 0 | 0 | 1.39 | 1.39 | 0
28 | Construction of road Atmaram Patil Chowk to Kalwa Naka | Mr. V.G. Surve | 0 | 0 | 0 | 100 | 0 | 150 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Const of ROB from Thane Belapur Road to APMC Market Turbhey | Mr. V.G. Surve | 0 | 0 | 0 | 50 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Construction of road MTHL to Mumbai Pune Expressway | Mr. Y.E. Sakhalkar | 0 | 0 | 0 | 200 | 200 | 500 | 250 | 0.00052 | 0 | 0 | 0 | 0 | 0 | 0.13 | 0.13 | 0.14 | 0.01
31 | Conservation, rejuvenation of Railadevi lake | Mr. V.G. Surve | 0 | 0 | 5.8 | 20.28 | 29.81 | 14.56 | 7.28 | 1.2473 | 27.32 | 36.4 | 0 | 0 | 0 | 9.0791 | 9.08 | 9.08 | 0
32 | Construction of Borivali – Gorai Bridge | Mr. P. J. Bhangare | 0 | 0 | 0.05 | 180 | 0 | 75 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Establishment of Covid Health Center at Valanai Village, Malad (W) Mumbai | NA | 0 | 0 | 0 | 0 | 6.14 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Construction of Tunnel from Orange Gate to Marine Drive | Mr. V.A. Jambhale | 0 | 0 | 3.22 | 1500 | 800 | 2400 | 1200 | 0.0093167 | 2.3 | 3.53 | 0 | 0 | 0 | 10 | 11.18 | 11.18 | 0
35 | Const. of Various Road in Thane, Mumbai, Navi Mumbai | Mr. B.H. Chavan, Mr. P.P. Bhandekar, Mr. S.S. Lokare, Mr. V.G. Surve, Mr. Y.E. Sakhalkar | 0 | 0 | 0 | 1000 | 8.25 | 2322 | 1161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | Versova - Virar Sea Link Project | Mr. V.A. Jambhale | 0 | 0 | 0 | 20 | 8.67 | 150 | 75 | 0.1716 | 8.26 | 10.43 | 0 | 0.93 | 0.93 | 0.93 | 12.87 | 12.87 | 0
37 | Improvement & Upgradation of Teen Hat Naka Junction at Thane | Mr. V.G. Surve | 0 | 0 | 0 | 100 | 0.25 | 150 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Construction of road at Yeoor Hills | Mr. V.G. Surve | 0 | 0 | 0 | 50 | 0.25 | 50 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Rehabilitation of affected villages Patan District Satara | Mr. B.H. Chavan | 0 | 0 | 0 | 24.5 | 1 | 161 | 80.5 | 0.12422 | 0 | 0.31 | 0 | 0 | 0 | 0 | 10 | 10 | 0
40 | Construction of Road from Vishwabharati Naka to Bhinar to Vadape | Mr. V.A. Jambhale | 0 | 0 | 0 | 25 | 0.5 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Water resource Projects (Surya , Kalu , Deharji ) | Mr. P. J. Bhangare | 175.31 | 228.73 | 927 | 1095.22 | 958.48 | 886 | 443 | 0.60414 | 648.39 | 903.73 | 0 | 182.58 | 198.22 | 267.6362 | 267.6362 | 267.6362 | 0
42 | Solid Waste Management | Mr. A.G. Korgaonkar | 0 | 0 | 0 | 24.3 | 21.1 | 131.5 | 65.75 | 0.1638 | 0 | 0 | 0 | 0 | 0 | 0 | 10.77 | 10.77 | 0

## town planning
Sr No. | Particulars | SE | 2020-21 | 2021-22 | 2022-2023 | B. E. 2023-24 | R. E. 2023-24 | B. E. 2024-25 | Proportionate | % Achievement (as compared to proportionate budget) | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01
1 | Construction of Late Balasaheb Thakrey National Memorial Phase II | Shri. Onkar Avinash (VSM, AVSM) | 0 | 0 | 0 | 0 | 0 | 150 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Ramabai Ambedkar Nagar slum redevelopment | Shri. Onkar Avinash (VSM, AVSM) | 0 | 0 | 0 | 0 | 0 | 600 | 300 | 0.0016667 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.55 | 0.05
1 | Kulgaon Badlapur Railway Station (SATIS) | Shri. Onkar Avinash (VSM, AVSM) | 0 | 0 | 0 | 0 | 0.5 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | New Town Development Authority for Influenced area of MTHL | Shri. Onkar Avinash (VSM, AVSM) | 0 | 0 | 0 | 0 | 0 | 60 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## transport and communication
Sr No. | Particulars | SE | 2020-21 | 2021-22 | 2022-2023 | B. E. 2023-24 | R. E. 2023-24 | B. E. 2024-25 | Proportionate | % Achievement (as compared to proportionate budget) | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01
1 | Mumbai Metro Rail Project: Versova - Andheri - Ghatkopar (sound resistance study, etc.) | Shri. Onkar Avinash (AVSM) | 12.36 | 2.6599 | 2.57 | 68.76 | 40 | 17 | 8.5 | 0.062353 | 30.06 | 118.64 | 0 | 0 | 1.69 | 3.9088 | 0.53 | 0.53 | 0
2 | Transfer and Acquition - Mumbai Metro Rail Project: Versova - Andheri - Ghatkopar (with arbitration costs) | Shri. Onkar Avinash (AVSM) | 0 | 0 | 0 | 0 | 0 | 4700 | 2350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Mumbai Metro Rail Project: Versova - Andheri - Ghatkopar - Homeguard building construction | Shri. Onkar Avinash (AVSM) | 0 | 3.18 | 12.84 | 11.7 | 7.49 | 15 | 7.5 | 0.092 | 7.48 | 7.48 | 0 | 0 | 0 | 0 | 0.69 | 0.69 | 0
4 | Matheran Funicular Railway | Shri. Onkar Avinash (AVSM) | 0 | 0 | 12.23 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Installation Informative and Cautionary Retro-Reflective Boards along Bandra Kurla Complex, Western Expressway | Shri. Onkar Avinash (AVSM) | 0 | 2.77 | 0 | 17.58 | 7.64 | 10.5 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ITS & Other Projects Under UMMTA | Shri. Onkar Avinash (AVSM) | 0 | 0 | 0 | 0.5 | 0.05 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Mahavir Nagar Metro Station - Pagoda - Gorai Village, Rope Way | Shri. Onkar Avinash (AVSM) | 0 | 0 | 74.69 | 0 | 0.1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Metro Road 7 - Foot over Bridge | Shri. Onkar Avinash (AVSM) | 0 | 0 | 0 | 113.7 | 100 | 73.1 | 36.55 | 0.22287 | 112.71 | 127.08 | 0 | 3.65 | 5.12 | 8.1458 | 8.1458 | 8.1458 | 0
9 | Implementation of Rapid Transit Service from Kanjurmarg to Badlapur | Shri. Onkar Avinash (AVSM) | 0 | 0 | 2.25 | 1 | 0.25 | 3.3 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Planning and Multi-Transport Integration Design for Mumbai Metro Stations (including Land Acquisition) -MMI | Shri. Onkar Avinash (AVSM) | 2.15 | 149.4862 | 211.92 | 260.56 | 180 | 780 | 390 | 0.012659 | -357.0748 | -357.0748 | 0 | 0.09 | 0 | 4.3771 | 4.9371 | 10.8071 | 5.87
11 | Implementation of access control system on WEH | Shri. Onkar Avinash (AVSM) | 0 | 7.84 | 0.05 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Pedestrian suspension bridge between City Park and Maharashtra Nature Park | Shri. Onkar Avinash (AVSM) | 0 | 0.05 | 0 | 67.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Construction of bridge connecting Nariman Point to Colaba / Cuffe Parade (including land acquisition) | Shri. Onkar Avinash (AVSM) | 0 | 0.18 | 0 | 100.51 | 5.8 | 100.54 | 50.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Construction of truck terminal at Mahul | Shri. Onkar Avinash (AVSM) | 0 | 0 | 0 | 46.75 | 0.8 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Impact study of Trafic For MTHL | Shri. Onkar Avinash (AVSM) | 0.67 | 0 | 0 | 39.44 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## metro projects
Sr No. | Particulars | SE | 2020-21 | 2021-22 | 2022-2023 | B. E. 2023-24 | R. E. 2023-24 | B. E. 2024-25 | Proportionate | % Achievement (as compared to proportionate budget) | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01
1 | Merto Project Line - 2 A : Dahisar D. N. Nagar | Soham Chandekar | 1319.6 | 661.7779 | 1302.4533 | 69.4076 | 400 | 200 | 100 | 0.55875 | 270.16 | 271.22 | 0 | 54.2 | 54.2 | 89.3731 | 55.875 | 55.975 | 0.1
2 | Merto Project Line - 2 B : D. N. Nagar to Mandale | Shashwat Kumar | 342.65 | 679.3532 | 908.6833 | 1463.82 | 2344.28 | 4302.64 | 2151.32 | 0.32651 | 936.08 | 1130.4 | 12.88 | 161.76 | 257.99 | 613.2211 | 702.4325 | 821.0775 | 118.645
3 | Merto Project Line - 3 : Colaba - Bandra - Seepz (MMRCL) | Soham Chandekar | 300 | 296 | 199.1 | 100 | 75 | 1 | 0.5 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Merto Project Line - 4 : Wadala - Kasarwadavali | Shashwat Kumar | 398.19 | 278.1115 | 647.97 | 2873.58 | 3023.35 | 4083.36 | 2041.68 | 0.18085 | 848.79 | 1014.67 | 29.8 | 104.94 | 124.83 | 234.1108 | 369.2408 | 432.41 | 63.1692
5 | Merto Project Line - 4 A : Kasarwadavali - Gaimukh | Soham Chandekar | 50.1 | 60.3685 | 88.57 | 403.2 | 227.01 | 530.2 | 265.1 | 0.26993 | 143.87 | 179.45 | -2.94 | 10.52 | 11.77 | 71.5572 | 71.5572 | 57.81 | -13.7472
6 | Merto Project Line - 5 : Thane - Bhivandi - Kalyan | Shashwat Kumar | 207.76 | 261.3881 | 262.76 | 1448.7106 | 1375.82 | 2186.68 | 1093.34 | 0.059153 | 335.69 | 366.7 | 4.49 | 19.79 | 19.87 | 35.6944 | 64.6744 | 68.74 | 4.0656
7 | Merto Project Line 6 : Swami Samarth Nagar -Vikhroli EEH | Soham Chandekar | 375.65 | 438.2321 | 183.76 | 943.13 | 437.28 | 1325.57 | 662.785 | 0.058172 | 279.86 | 315.72 | 8.72 | 31.6 | 31.61 | 38.2457 | 38.5557 | 62.32 | 23.7643
8 | Merto Project Line - 7 : Andheri (East) - Dahisar (E) | Shashwat Kumar | 736.2 | 901.0345 | 730.8533 | 681.48 | 817.73 | 171.85 | 85.925 | 4.149 | 145.61 | 149.73 | 0 | 2.74 | 2.74 | 356.4891 | 356.4991 | 361.7641 | 5.265
9 | Metro Project Line - 8: Airport Metro (CSMIA) to N.M.M.I.A. | Soham Chandekar | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Merto Project Line - 9 : Dahisar-Mira Bhayender - 7A Andheri to CSMIA Airport | Shashwat Kumar | 207.37 | 301.8731 | 430.42 | 1160.9875 | 1602.18 | 2359.96 | 1179.98 | 0.17208 | 543.25 | 656.91 | -6.08 | 40.12 | 94.89 | 189.8514 | 203.0514 | 206.96 | 3.9086
11 | Merto Project Line- 10 : Gaimukh to Shivaji Chowk (Mira Bhayandar) | Soham Chandekar | 0.84 | 0 | 0 | 100 | 0.2 | 1.2 | 0.6 | 3.5 | 1.7 | 1.71 | 0.01 | 2.04 | 2.04 | 2.04 | 2.1 | 2.2 | 0.1
12 | Merto Project Line - 12 : Kalayn - Taloja | Shashwat Kumar | 0 | 0 | 1.44 | 500 | 446.91 | 1510.58 | 755.29 | 0.083107 | 9.89 | 9.98 | 0.05 | 3.97 | 3.97 | 62.13 | 62.77 | 63.64 | 0.87
13 | Merto Project Line - 13 : Ghodbandar - Virar | Soham Chandekar | 0 | 0 | 0 | 2 | 0.5 | 1.5 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Metro Project Line - 14: Kanjur - Badlapur | Shashwat Kumar | 0 | 0 | 0 | 0 | 0 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Maha Mumbai Metro Rail Operation Ltd | Soham Chandekar | [5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0
16 | Metro Bhavan | Shashwat Kumar | 0.82 | 0 | 6.15 | 25 | 60 | 300 | 150 | 0.30576 | 31.35 | 57.39 | -1 | -1 | 14.48 | 20.18 | 45.8637 | 57.3837 | 11.52
17 | Metro - Staff Quarters | Soham Chandekar | 0 | 3.18 | 23.5 | 60 | 40 | 150 | 75 | 0.20427 | 33.7414 | 40.0514 | 0 | 7.38 | 15.03 | 15.03 | 15.32 | 24.15 | 8.83
18 | Integrated digital delivery | Shashwat Kumar | 0 | 0 | 0 | 100 | 0 | 50 | 25 | 0.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 1.15 | 0.06

## Mono PIU
Sr No. | Particulars | SE | 2020-21 | 2021-22 | 2022-2023 | B. E. 2023-24 | R. E. 2023-24 | B. E. 2024-25 | Proportionate | % Achievement (as compared to proportionate budget) | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01
1 | Mono Rail Project | Manoj Vispute | 11.94 | 29.7 | 92.7177 | 290.51 | 111.34 | 360.64 | 180.32 | 1.0058 | 5.71 | -71.32 | 0 | 0 | 0 | 0 | 181.37 | 34.39 | -146.98
2 | Mono Rail Project - Arbitration Costs | Manoj Vispute | 0 | 0 | 0 | 0 | 362.06 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 160 | 0